## All other (hidden)
Sr. No.​ | Solar plant | Consumer​ | DISCOM​ | MW AC | MWp DC | CD | Feeder | ABT Meter | PPA Date | OA-CA | DISCOM NOC | LT-2 | EE nomination | BPTA | UPSLDC Registration | Remarks | Anticipated Date for LTOA Power Delivery | BD Team | Consultant | Process started on | Deadline of power supply
4 | SS8PL-Pailani II | Hilltop | MVVNL | 2.5 | 3.75 | 2.5 | Mixed | Y |  | Y |  | Y |  |  |  | Fee payment to UPSLDC pending, MRI data pending. Equity infusion pending |  | Amritesh | Topnotch
5 | SS9PL-Mau | Jaypee Healthcare | PVVNL​ | 2.67 | 4 | 3 | Independent | Y |  | Y |  | Y |  |  |  | Registration pending because consumer does not have valid CEIG certificate MRI data, Constraints because of Name change |  | Paurush | Topnotch
[5 empty] | WCL- Signatory changed | delay in providing signed letters |  |  |  |  | DISCOM NOC | LT-1 Application
2026-03-17
396000
392832

## Elin (hidden)
Solar plant | SS5PL-Pinahat
Consumer​ | Elin
DISCOM​ | PVVNL​
MW AC | 1.135
MWp DC | 1.7025
CD | 3.5
Feeder | Independent
ABT Meter | Y
PPA Date | 2025-10-28
OA-CA | 2025-12-30
Request letter fod DISCOM NOC sent | 2025-12-04
Request letter for DISCOM NOC received on | 2026-01-02
Request for LT-1 fee payment | 2026-01-22
LT-1 fee payment | 2026-01-23
DISCOM NOC | 2025-03-17
LT-1 application | 2025-03-17
LT-2 | 2025-04-28
EE nomination | 2026-06-03
BPTA | 2026-06-29
UPSLDC Registration | pending

## UP LTOA approvals
Sr.no. | SPV | Location | Consumer | Capacity (MWp) | Tariff (INR / Unit) | Capacity (MW) | DISCOM | S/s | Feeder | ABT Meter | SLD | CEIG | LTOA PPA | OA-CA | DISCOM NOC | LT-2 | EE Nomination | BPTA/BPWA | Consumer Registration | Power Delivery | WBA | Remarks | BD Team | Consultant | Process started on | End Date
1 | Netra Renewable Energy Pvt Ltd | Erach | Max Square Ltd | 5.5 | 3.49 | 3.6667 | PVVNL​ |  | 33kV Mixed | Y | Y | Y | 2026-06-25 | 2026-08-21 | - | - |  | - | - | 2026-02-10 |  | STOA power supply | Paurush | AR Electro |  |  |  |  | PO Pending
2 | Netra Renewable Energy Pvt Ltd | Erach | Apollo Coated Products | 11 | 3.23 | 7.3333 | PVVNL​ |  | 33kV Independent | Y | Y | Y | 2024-05-28 | 2025-09-04 | 2025-10-16 | 2025-12-05 | 2026-01-06 | 2026-01-29 | Y | 2026-02-19 | 2026-06-16 |  | Paurush | AR Electro
3 | Netra Renewable Energy Pvt Ltd | Erach | Bisleri International Ltd | 2.5 | 3.5 | 1.6667 | PVVNL​ |  | 33kV Mixed | Y | Y | Y | 2025-09-30 | 2025-11-01 | 2026-01-22 | 2026-02-10 | 2026-03-19 | 2026-05-02 | Y | 2026-06-01 | 2026-07-21 |  | Amritesh | AR Electro
4 | Netra Renewable Energy Pvt Ltd | Erach | LG Electronics | 11 | 3.2 | 7.3333 | NPCL |  | 33kV Independent | Y | Y | Y | 2026-01-19 | 2026-03-31 | 2026-03-20 | 2026-04-16 | NPCL | 2026-05-12 | Y | 2026-05-18 | 2026-06-16 |  | Amritesh | Topnotch
5 | Netra Renewable Energy Pvt Ltd | Erach | GK Winding Wires | 2.5 | 3.28 | 1.6667 | NPCL |  | 33kV Mixed | Y | Y | Y | 2025-11-17 | 2026-03-12 | 2026-03-09 | 2026-04-16 | NPCL | 2026-06-02 | Y | 2026-06-14 | 2026-06-16 |  | Paurush | AR Electro
6 | Netra Renewable Energy Pvt Ltd | Erach | SIFY Infinit Spaces Ltd | 30 | 3.24 | 18 | PVVNL​ |  | 33kV Mixed | Y | Y | Y | 2026-03-26 | 2026-02-06 | 2026-02-23 | 2026-04-28 | 2026-06-03 | 2026-07-03 | pending | 2026-06-01 |  | Multiple queries in LTOA consumer registration application STOA power supply from 1st June for 14 MW | Amritesh | Topnotch
7 | Netra Renewable Energy Pvt Ltd | Erach | INOX Air Products Ltd | 4.2 | 3.19 | 4.2 | NPCL |  | 33kV Mixed | Y | Y | Y | 2026-03-02 | 2026-05-25 | 2026-05-01 | 2026-07-30 | NPCL |  |  | 2026-06-19 |  | STOA Power supply | Kartikeya | AR Electro
8 | Netra Renewable Energy Pvt Ltd | Erach | International Tobacco | 3.2 | 3.26 | 2.1333 | PVVNL​ |  | 33kV Independent | Y | Y | Y | 2026-04-15 | 2025-11-07 | 2026-05-30 | 2026-07-04 | 2026-08-03 | 2026-08-18 |  | 2026-09-01 |  | EE nomination pending | Paurush | AR Electro | 2026-05-12 | 7 months from 1st equity | 583.5 | 522
9 | Netra Renewable Energy Pvt Ltd | Erach | Jakson Engineers Ltd | 3.5 | 3.35 | 2.3333 | NPCL | 33/11 EES 10 S/s Gr Noida | 11kV Independent |  |  |  | 2025-09-30: 2026-03-13; 2025-11-01: pending |  | 2026-11-01 |  | LT-1 submitted with UPPTCL | Paurush | Topnotch | [5 empty] | PO Pending
10 | Netra Renewable Energy Pvt Ltd | Erach | Haldiram C-1 | 7 | 3.39 | 4.6667 | PVVNL​ | 132 kV s/s Sec 67 Noida | 33kV Mixed | Y | Y |  | 2025-09-30: 2025-07-07; 2025-11-01: 2026-08-10; 2026-01-22: 2026-08-10 |  |  |  |  | Vinod | Topnotch | [5 empty] | PO Pending
11 | Netra Renewable Energy Pvt Ltd | Erach | SKVR | 6.3 | 3.19 | 2 | PVVNL​ | [5 empty] | 2025-09-30: 2025-12-15; 2025-11-01: pending |  |  |  |  | Amritesh | Topnotch
12 | Sunsure Energy Pvt Ltd | Charkhari | UTCL-Aligarh | 30 | 2.95 | 20 | DVVNL |  | 132 kV Independent | Y | Y | Y | 2026-03-18 | Yes 8.5 MVA, to be revised | 2026-06-03 | pending | [6 empty] | Vinod Sir | Topnotch
13 | Sunsure Energy Pvt Ltd | Charkhari | UTCL-Dadri | 12 | 2.95 | 8 | PVVNL |  | 132 kV Independent | Y | Y | Y | 2026-03-19 | Yes, to be revised 14 MVA | 2026-06-29 | pending | [6 empty] | Vinod Sir | Topnotch
14 | Sunsure Energy Pvt Ltd | Charkhari | UTCL-Shahjahanpur | 18 | 2.95 | 12 | MVVNL |  | 132 kV Independent | Y | Y | Y | 2026-03-20 | Yes, to be revised 12 MVA | 2026-06-09 | pending | [6 empty] | Vinod Sir | Topnotch
15 | Sunsure Solarpark Five Pvt Ltd | Pinahat | Elin Electronics Ltd | 1.7025 |  | 1.135 | PVVNL​ | [5 empty] | 2025-10-28 | 2025-12-30 | 2025-03-17 | 2025-04-28 | 2026-06-03 | 2026-06-29 | Y | 2026-07-26 | pending |  | Paurush | AR Electro |  |  |  |  | PO Pending
16 | Sunsure Solarpark Six Pvt Ltd | Augasi | Wonder Cement Ltd | 8.68 |  | 6.2 | DVVNL |  | 132 kV Independent |  |  |  | 2026-03-06 | 2024-07-26 | 2026-05-29 | 2026-07-03 | 2026-07-21 | 2026-08-05 | 2026-08-12 | 2026-08-15 | pending |  | Vinod Sir | AR Electro | 2026-04-30
17 | Sunsure Solarpark Sixteen Pvt Ltd | Gursarai | Jakson Engineers Ltd | 1.2 |  | 0.8 | PVVNL​ | 33/11KV, A BLOCK HOSIERYCOMPLEX SUBSTATION | 11kV Mixed |  |  |  | 2026-03-13 | 2026-05-28 | 2026-05-21 | 2026-06-12 | 2026-07-15 | 2026-08-14 | Y | 2026-08-27 | pending |  | Paurush | Topnotch | 2026-04-08
17 | Sunsure Solarpark Sixteen Pvt Ltd | Gursarai | Minda Corporation Ltd | 0.8 | PVVNL​ | 1.1 |  |  | 2026-03-13 |  |  |  | 2025-09-30: 2026-07-22; 2025-11-01: pending; 2026-05-02: BPTA, AMR awaited | Paurush | Topnotch | 2026-04-08
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shared with CO team on 29 July 26
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SHARED WITH US ON 21 AUG
Note on N20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shared with us on 14 aug

## UTCL STOA Cost
Pre Requisites | Consultancy Cost | GST | Statutory Fee |  | Total Cost for One unit and One month | 173200
ST-11 NOCs | 50000 | 9000 | 0 |  | Total Cost for three unit and One month | 519600
UPSLDC-R annual registration (Intra State) | 20000 | 3600 | 15000 |  | Total Cost for three unit and Four month | 1200000
Total | 70000 | 12600 | 15000 | 97600
STOA transaction cost per month per unit | Consultancy Cost | GST | Statutory Fee
Application cost | 20000 | 3600 | 7000
Daily operating charges (30 days) |  |  | 45000
Total | 20000 | 3600 | 52000 | 75600

## NREPL-approval timeline (hidden)
| Bisleri (PVVNL) | Sify (PVVNL) | GK Winding (NPCL) | LG (NPCL)
OA-CA | 2025-11-10 | 2026-02-06 | 2026-03-17 | 2026-03-31
DISCOM NOC | 2026-01-22 | 2026-02-23 | 2026-03-17 | 2026-03-20
Letter from UPPTCL to NPCL | Not required | Not required | 2026-02-11
LT-1 | 2026-01-27 | 2026-03-16 | 2025-12-19 | 2026-02-12
LT-2 | 2026-02-10 | 2026-04-28 | 2026-04-28 | 2026-04-14
BPTA EE nomination | 2026-03-19 | pending | Not required | Not required
BPTA signing | Final signing pending with UPPTCL |  |  | Singing pending with NPCL

## Sheet1 (hidden)
eass | upsldc-r | registration date
NREPL | Erach | Intra-State | 55 | 2025-08-26
NREPL | Erach | ISTS | 30 | 2025-08-25
SS16PL | Gursarai | Intra-State | 3 | 2025-08-26
SS6PL | Augasi | Intra-State | 35 | 2025-08-29
SS5PL | Pinahat | Intra-State | 7.965 | 2025-08-29
SS9PL | Mau | Intra-State | 10 | 2025-08-26

## JSL Timeline (hidden)
Approval | Date | Remarks
Initial PPA | 2025-02-20
DISCOM NOC | 2025-03-11
LT-1 Application | 2025-03-13
LT-2 approved | 2025-03-29
PPA amended | 2025-08-26
LT-2 Cancellation Request Letter | 2025-09-03 | Scanned copy received on this date; original couriered to Lucknow.
Interim Period |  | UPPTCL sought internal clarification on whether LT-2 could be cancelled after 45 days of issuance and whether transmission charges would apply if the 45-day window was extended. We followed up with them regularly. The review period extended over nearly two months (including Dussehra and Diwali holidays). UPPTCL ultimately concluded that no regulation or office order restricts LT-2 cancellation beyond 45 days from issuance. After reviewing the regulations, UPPTCL advised us to request capacity revision in the approved LT-2 instead of pursuing cancellation and resubmitting LT-1.
LT-2 quantum revision requested on | 2025-11-18
LT-2 revised | 2025-11-19
Draft letters reagrding BPTA | 2025-11-20
Scanned copy of BPTA request letters as received from JSL | 2025-11-27
EE nomination for BPTA signing | 2026-01-27 | JSL had billing/accounting issues with PVVNL which delayed the nomination of the Executive Engineer (EE). The EE nomination was completed after resolution of the billing issue.
BPTA signed and executed | 2026-02-16 | BPTA signed by all three parties in submitted to UPPTCL
UPSLDC consumer registration | Second week of March 26
SCOD | 5 months from the date of first tranche of equity infusion | As per Clause 4.3 of the original PPA; clause remains unchanged in the amended PPA.
Grace period | One month from SCOD or revised SCOD